## Sheet1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort
1 | US:03 | 1 | Updating the Category | Varsha |  | 1 day |  |  | 2 days
2 | US:02 | 1 | Creating the Category | Ritika |  | 1 day |  |  | 2 days
3 | US:05 | 1 | List all books | Aarthi |  | 1 day |  |  | 2 days
4 | US:04 | 1 | deleting the book | Sakshi |  | 1 day |  |  | 2 days
5 | US:06 | 1 | editing the book | Sai Sravanthi |  | 1 day |  |  | 2 days
6 | US:07 | 1 | List all categories | Sushmitha |  | 1 day |  |  | 2 days
7 | US:01 | 1 | deleting category | Shreya |  | 1 day |  |  | 2 days
8 | US:08 | 1 | Creating the book | Manasa |  | 1 day |  | created class diagrams and working on data jpa | 2 days